## work order tracker
Deal name masked | Customer Name Code | Serial # | Nature of Work | Last executed month of recurring project | Execution Status | Data Delivery Date | Date of PO/LOI | Document Type | Probable Start Date | Probable End Date | BD/KAM Personnel code | Sector | Type of Work | Is any Skylark software platform part of the client deliverables in this deal? | Last invoice date | latest invoice no. | Amount in Rupees (Excl of GST) (Masked) | Amount in Rupees (Incl of GST) (Masked) | Billed Value in Rupees (Excl of GST.) (Masked) | Billed Value in Rupees (Incl of GST.) (Masked) | Collected Amount in Rupees (Incl of GST.) (Masked) | Amount to be billed in Rs. (Exl. of GST) (Masked) | Amount to be billed in Rs. (Incl. of GST) (Masked) | Amount Receivable (Masked) | AR Priority account | Quantity by Ops | Quantities as per PO | Quantity billed (till date) | Balance in quantity | Invoice Status | Expected Billing Month | Actual Billing Month | Actual Collection Month | WO Status (billed) | Collection status | Collection Date | Billing Status
Scooby-Doo | WOCOMPANY_002 | SDPLDEAL-075 | One time Project |  | Completed | 2025-09-27 | 2025-10-29 | Purchase Order | 2025-05-31 | 2025-06-03 | OWNER_003 | Mining | Raw images/videography | NONE | 2026-01-14 | SDPL/FY25-26/916 | 264398.08 | 311989.7344 |  | 0 |  | 264398.08 | 311989.7344 | 0 |  |  | 5360 HA |  | 5360 | [7 empty] | Update Required
Appa | WOCOMPANY_038 | SDPLDEAL-101 | Proof of Concept |  | Not Started |  | 2025-07-31 | Purchase Order | 2025-08-11 | 2025-08-15 | OWNER_002 | Powerline | Powerline Inspection |  |  |  | 154150 | 181897 |  | 0 |  | 154150 | 181897 | 0 |  |  | 4 |  | 4 |  |  |  |  | Open
Sakura | WOCOMPANY_002 | SDPLDEAL-002 | Monthly Contract | Dec | Executed until current month | 2025-12-31 | 2025-05-16 | Purchase Order | 2025-05-01 | 2026-04-30 | OWNER_003 | Mining | Volumetric survey | NONE |  |  | 2984097.36 | 3521234.8848 | 23959.6825 | 28272.4253 |  | 2960137.6775 | 3492962.4595 | 28272.4253 |  |  | 3000 |  | 3000 |  |  |  |  | Open |  |  | Partially Billed
Sakura | WOCOMPANY_002 | SDPLDEAL-003 | One time Project |  | Completed |  | 2025-05-08 | Purchase Order | 2025-05-20 | 2025-05-31 | OWNER_003 | Mining | Topography Survey: RGB | NONE | 2025-09-15 | SDPL/FY25-26/449 | 184980 | 218276.4 | 184980 | 218276.4 | 66880.1356 | 0 | 0 | 151396.2644 |  |  | 600 |  | 600 | Not billed yet |  |  |  | Open
SpongeBob | WOCOMPANY_032 | SDPLDEAL-004 | One time Project |  | Completed |  | 2025-05-06 | LOA/LOI | 2025-05-24 | 2025-06-20 | OWNER_003 | Powerline | Powerline Inspection | NONE |  |  | 1132250.248 | 1336055.2926 | 1215157.5441 | 1433885.902 |  | -82907.2961 | -97830.6094 | 1433885.902 | Priority |  | 59.33 |  | 59.33 |  |  |  |  | Open |  |  | BIlled
Edward Elric | WOCOMPANY_008 | SDPLDEAL-005 | One time Project |  | Completed |  | 2025-05-16 | Purchase Order | 2025-05-20 | 2025-05-31 | OWNER_003 | Renewables | Hydrology | NONE | 2025-07-18 | SDPL/FY25-26/359 | 135652 | 160069.36 | 135652 | 160069.36 | 160069.36 | 0 | 0 | 0 |  |  | 1 | 1 | 0 | Fully Billed |  |  |  | Closed
Pumbaa | WOCOMPANY_047 | SDPLDEAL-001 | Annual Rate Contract | June | Ongoing |  | 2025-05-15 | Purchase Order | 2025-05-19 | 2025-11-19 | OWNER_005 | Renewables | Others | SPECTRA | 2025-09-06 | SDPL/FY25-26/431 | 3995568 | 4714770.24 | 3662604 | 4321872.72 | 1405108.08 | 332964 | 392897.52 | 2916764.64 |  |  | 12 | 2 | 10 | Partially Billed |  |  |  | Open
Sakura | WOCOMPANY_002 | SDPLDEAL-006 | Monthly Contract | November | Executed until current month |  | 2025-05-21 | Purchase Order | 2025-05-01 | 2026-04-30 | OWNER_003 | Mining | Topography Survey: RGB | NONE | 2025-06-16 | SDPL/FY25-26/064 | 727588 | 858553.84 | 151417.1918 | 178672.2863 | 178672.182 | 576170.8082 | 679881.5537 | 0.10433 |  |  | 1600 |  | 1600 | Partially Billed |  |  |  | Open
Sakura | WOCOMPANY_002 | SDPLDEAL-007 | Monthly Contract | Dec | Executed until current month |  | 2025-05-22 | Purchase Order | 2025-05-20 | 2026-04-30 | OWNER_003 | Mining | Topography Survey: RGB | NONE | 2025-09-06 | SDPL/FY25-26/435 | 2293752 | 2706627.36 | 1742808.4436 | 2056513.9634 | 1225606.682 | 550943.5564 | 650113.3966 | 830907.2814 |  |  | 4800 |  | 4800 | Partially Billed |  |  |  | Open
Alias_160 | WOCOMPANY_051 | SDPLDEAL-008 | One time Project |  | Completed | 2025-05-28 | 2025-04-10 | Purchase Order | 2025-04-20 | 2025-05-31 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-23 | SDPL/FY25-26/365 | 126649.64 | 149446.5752 | 81360.37 | 96005.2366 |  | 45289.27 | 53441.3386 | 96005.2366 |  | 447.1706 | 460 |  | 460 | Fully Billed |  | July |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-009 | One time Project |  | Completed | 2025-05-30 | 2025-04-10 | Purchase Order | 2025-04-15 | 2025-05-31 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-06 | SDPL/FY25-26/385 | 1198053.8 | 1413703.484 | 680159.9172 | 802588.7024 | 397840.8515 | 517893.8828 | 611114.7816 | 404747.8508 |  | 2424.42 | 2500 |  | 2500 | Fully Billed |  | August |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-010 | One time Project |  | Completed | 2025-06-10 | 2025-04-10 | Purchase Order | 2025-04-14 | 2025-05-31 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-06-27 | SDPL/FY25-26/096 | 112652.82 | 132930.3276 | 112652.82 | 132930.3276 |  | 0 | 0 | 132930.3276 |  | 629.83 | 630 |  | 630 | Fully Billed |  | June |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-011 | One time Project |  | Completed | 2025-05-20 | 2025-04-10 | Purchase Order | 2025-04-10 | 2025-05-31 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-06 | SDPL/FY25-26/382 | 643730.4 | 759601.872 | 593662.48 | 700521.7264 | 641154.9235 | 50067.92 | 59080.1456 | 59366.8029 |  | 3319.81 | 3600 |  | 3600 | Fully Billed |  | August |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-012 | One time Project |  | Completed | 2025-06-17 | 2025-04-10 | Purchase Order | 2025-04-14 | 2025-06-16 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-23 | SDPL/FY25-26/366 | 770750 | 909485 | 380158.564 | 448587.1055 | 371722.8964 | 390591.436 | 460897.8945 | 76864.2091 |  | 2125.655 | 2500 |  | 2500 | Fully Billed |  | July |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-013 | One time Project |  | Completed | 2025-05-13 | 2025-04-10 | Purchase Order | 2025-04-15 | 2025-05-31 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-06 | SDPL/FY25-26/383 | 214576.8 | 253200.624 | 172555.51 | 203615.5018 | 186359.8768 | 42021.29 | 49585.1222 | 17255.625 |  | 964.8312 | 1200 |  | 1200 | Fully Billed |  | August |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-014 | One time Project |  | Completed | 2025-05-30 | 2025-04-10 | Purchase Order | 2025-04-09 | 2025-06-20 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-09-24 | SDPL/FY25-26/475 | 250339.6 | 295400.728 | 177469.3187 | 209413.7961 | 191666.4104 | 72870.2813 | 85986.9319 | 17747.3857 |  | 922.484 | 1400 |  | 1400 | Fully Billed |  | September |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-015 | One time Project |  | Completed | 2025-05-03 | 2025-04-10 | Purchase Order | 2025-04-22 | 2025-06-20 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-06 | SDPL/FY25-26/384 | 109791.796 | 129554.3193 | 109791.796 | 129554.3193 | 118573.9065 | 0 | 0 | 10980.4128 |  | 613.57 | 614 |  | 614 | Fully Billed |  | August |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-016 | One time Project |  | Completed | 2025-05-06 | 2025-04-10 | Purchase Order | 2025-04-25 | 2025-06-13 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-09-08 | SDPL/FY25-26/437 | 210799.5084 | 248743.4199 | 210799.5084 | 248743.4199 | 189719.4712 | 0 | 0 | 59023.9487 | Priority | 1213.9 | 1178.88 |  | 1178.88 | Fully Billed |  | September |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-017 | One time Project |  | Completed | 2025-05-13 | 2025-04-10 | Purchase Order | 2025-04-25 | 2025-05-31 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-10 | SDPL/FY25-26/133 | 62584.9 | 73850.182 | 62584.9 | 73850.182 | 67591.914 | 0 | 0 | 6258.268 |  | 348.2 | 350 |  | 350 | Fully Billed |  | July |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-018 | One time Project |  | Completed | 2025-05-06 | 2025-04-10 | Purchase Order | 2025-04-28 | 2025-05-31 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-06-29 | SDPL/FY25-26/099 | 260360.5832 | 307225.4882 | 260353.184 | 307216.7571 | 281181.8333 | 7.3992 | 8.7311 | 26034.9238 |  | 1437.2 | 1456 |  | 1456 | Fully Billed |  | July |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-019 | One time Project |  | Completed | 2025-06-14 | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-05-30 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-06-27 | SDPL/FY25-26/110 | 157535.134 | 185891.4581 | 157399.2354 | 185731.0977 | 185891.3348 | 135.8986 | 160.3604 | -160.2371 |  | 880.27 | 881 |  | 881 | Fully Billed |  | July |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-020 | One time Project |  | Completed | 2025-06-03 | 2025-04-10 | Purchase Order | 2025-05-02 | 2025-05-30 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-19 | SDPL/FY25-26/360 | 227987.85 | 269025.663 | 215828.498 | 254677.6276 | 233094.3832 | 12159.352 | 14348.0354 | 21583.2444 |  | 1206.67 | 1275 | 1207 | 68 | Fully Billed |  | July |  | Closed
Mojo Jojo | WOCOMPANY_036 | SDPLDEAL-021 | One time Project |  | Completed | 2025-06-24 | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-05-31 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-08 | SDPL/FY25-26/399 | 151275.4108 | 178504.9847 | 125206.796 | 147744.0193 | 147743.526 | 26068.6148 | 30760.9655 | 0.49328 |  | 383.54 | 446.07 |  | 446.07 | Fully Billed |  | August |  | Closed
Mojo Jojo | WOCOMPANY_036 | SDPLDEAL-022 | One time Project |  | Completed | 2025-05-07 | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-05-31 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-05 | SDPL/FY25-26/143 | 1164911.55 | 1374595.629 | 1138011.7584 | 1342853.8749 | 1342853.6776 | 26899.7916 | 31741.7541 | 0.19731 |  | 3352.9362 | 3435 |  | 3435 | Fully Billed |  | August |  | Closed
Mojo Jojo | WOCOMPANY_036 | SDPLDEAL-024 | One time Project |  | Completed | 2025-06-07 | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-05-31 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-06 | SDPL/FY25-26/389 | 371860.3612 | 438795.2262 | 365246.7096 | 430991.1173 | 430990.772 | 6613.6516 | 7804.1089 | 0.3453 |  |  | 662.27 |  | 662.27 | Fully Billed |  | August |  | Closed
Mojo Jojo | WOCOMPANY_036 | SDPLDEAL-023 | One time Project |  | Completed | 2025-06-24 | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-05-31 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-07 | SDPL/FY25-26/394 | 440190.74 | 519425.0732 | 396450.3692 | 467811.4357 | 467810.7204 | 43740.3708 | 51613.6375 | 0.71526 |  | 1073.63 | 1180 |  | 1180 | Fully Billed |  | September |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-025 | One time Project |  | Completed | 2025-07-10 | 2025-04-10 | Purchase Order | 2025-05-07 | 2025-06-15 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-25 | SDPL/FY25-26/371 | 170274.09 | 200923.4262 | 170274.09 | 200923.4262 |  | 0 | 0 | 200923.4262 |  | 952.24 | 952.24 |  | 952.24 | Fully Billed |  | July |  | Closed
Tanjiro | WOCOMPANY_005 | SDPLDEAL-026 | One time Project |  | Completed | 2025-06-11 | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-05-30 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-07 | SDPL/FY25-26/395 | 183130.2 | 216093.636 | 179510.758 | 211822.6944 | 17951.6924 | 3619.442 | 4270.9416 | 193871.002 |  | 808.6642 | 825 |  | 825 | Fully Billed |  | July |  | Closed
Tanjiro | WOCOMPANY_005 | SDPLDEAL-027 | One time Project |  | Completed | 2025-06-16 | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-05-30 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-08 | SDPL/FY25-26/398 | 937848.6 | 1106661.348 | 937848.6 | 1106661.348 |  | 0 | 0 | 1106661.348 |  | 4178.4382 | 4225 |  | 4225 | Fully Billed |  | August |  | Closed
Tanjiro | WOCOMPANY_005 | SDPLDEAL-028 | One time Project |  | Completed | 2025-06-16 | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-05-30 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-07 | SDPL/FY25-26/396 | 355161.6 | 419090.688 | 336437.9244 | 396996.7508 |  | 18723.6756 | 22093.9372 | 396996.7508 |  | 1505.6458 | 1600 |  | 1600 | Fully Billed |  | August |  | Closed
Tanjiro | WOCOMPANY_005 | SDPLDEAL-029 | One time Project |  | Completed | 2025-06-13 | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-05-30 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-06 | SDPL/FY25-26/392 | 358830.8633 | 423420.4187 | 358830.37 | 423419.8366 |  | 0.49328 | 0.58207 | 423419.8366 |  | 1626.3205 | 1616.53 |  | 1616.53 | Fully Billed |  | August |  | Closed
Armin | WOCOMPANY_020 | SDPLDEAL-030 | One time Project |  | Completed | 2025-05-09 | 2025-04-10 | Purchase Order | 2025-04-15 | 2025-05-30 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-06-24 | SDPL/FY25-26/084 | 135488.712 | 159876.6801 | 135489.2176 | 159877.2768 | 159876.9808 | -0.50561 | -0.59662 | 0.29597 |  | 396.22 | 406 |  | 406 | Fully Billed |  | June |  | Closed
Armin | WOCOMPANY_020 | SDPLDEAL-031 | One time Project |  | Completed | 2025-05-09 | 2025-04-10 | Purchase Order | 2025-04-15 | 2025-05-30 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-06-24 | SDPL/FY25-26/086 | 236813.8624 | 279440.3576 | 236813.8624 | 279440.3576 | 4737.9544 | 0 | 0 | 274702.4032 |  | 705.02 | 711.23 |  | 711.23 | Fully Billed |  | June |  | Closed
Armin | WOCOMPANY_020 | SDPLDEAL-032 | One time Project |  | Completed | 2025-05-09 | 2025-04-10 | Purchase Order | 2025-04-15 | 2025-05-30 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-06-24 | SDPL/FY25-26/085 | 382095.9212 | 450873.187 | 382095.9212 | 450873.187 | 450873.9516 | 0 | 0 | -0.76458 |  | 1144.13 | 1147.56 |  | 1147.56 | Fully Billed |  | June |  | Closed
Jessie | WOCOMPANY_043 | SDPLDEAL-033 | Annual Rate Contract | June | Completed | 2025-06-15 | 2025-04-10 | Purchase Order | 2025-04-21 | 2025-05-31 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-21 | SDPL/FY25-26/418 | 755939.268 | 892008.3362 | 545913.7159 | 644178.1848 | 383312.436 | 210025.5521 | 247830.1515 | 260865.7488 | Priority | 6539.578 | 5838 |  | 5838 | Partially Billed |  | August |  | Closed
Naruto | WOCOMPANY_001 | SDPLDEAL-034 | One time Project |  | Completed |  | 2025-05-27 | Purchase Order | 2025-05-27 | 2025-06-30 | OWNER_003 | Renewables | Hydrology | NONE | 2025-09-16 | SDPL/FY25-26/455 | 308300 | 363794 | 308300 | 363794 | 120853.6 | 0 | 0 | 242940.4 | Priority |  | 1 |  | 1 | Fully Billed |  |  |  | Closed
Inosuke | WOCOMPANY_045 | SDPLDEAL-035 | Proof of Concept |  | Ongoing |  | 2025-05-13 | LOA/LOI | 2025-06-01 | 2025-06-30 | OWNER_003 | Railways | Road/rail survey | NONE |  |  | 1.2332 | 1.4552 |  | 0 |  | 1.2332 | 1.4552 | 0 |  |  | 1 |  | 1 |  |  |  |  | Open |  |  | Not Billable
Alias_162 | WOCOMPANY_052 | SDPLDEAL-037 | Annual Rate Contract | Dec | Completed | 2025-06-18 | 2025-04-25 | Purchase Order | 2025-06-04 | 2025-06-30 | OWNER_001 | Mining | Topography Survey: RGB | NONE |  |  | 2250751.5492 | 2655886.8281 | 2158261.9192 | 2546749.0646 |  | 92489.63 | 109137.7634 | 2546749.0646 | Priority |  | 300 |  | 300 | Partially Billed |  | July |  | Open
Alias_162 | WOCOMPANY_052 | SDPLDEAL-038 | One time Project |  | Completed | 2025-06-22 | 2025-04-10 | Purchase Order | 2025-06-12 | 2025-06-30 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-01 | SDPL/FY25-26/372 | 476015.2 | 561697.936 | 476382.6936 | 562131.5784 | 562132.0224 | -367.4936 | -433.6424 | -0.44395 |  |  | 643 |  | 643 | Fully Billed |  | July |  | Closed
Alphonse | WOCOMPANY_009 | SDPLDEAL-040 | One time Project |  | Completed | 2025-09-23 | 2025-06-11 | Purchase Order | 2025-06-16 | 2025-07-04 | OWNER_001 | Renewables | Topography Survey: RGB | NONE |  |  | 1426208.132 | 1682925.5958 |  | 0 |  | 1426208.132 | 1682925.5958 | 0 |  |  | 2057 Acr |  | 2057 | Not billed yet |  |  |  | Open
Alphonse | WOCOMPANY_009 | SDPLDEAL-041 | One time Project |  | Completed | 2025-06-11 | 2025-06-11 | Purchase Order | 2025-06-02 | 2025-06-13 | OWNER_001 | Renewables | Hydrology, Topography Survey: RGB | NONE | 2025-06-17 | SDPL/FY25-26/068 | 443952 | 523863.36 | 443952 | 523863.36 | 523863.36 | 0 | 0 | 0 |  |  | 1 | 1 | 0 | Fully Billed |  | June |  | Closed
Alphonse | WOCOMPANY_009 | SDPLDEAL-042 | One time Project |  | Completed |  | 2025-06-11 | Purchase Order | 2025-06-02 | 2025-06-11 | OWNER_001 | Renewables | Topography Survey: RGB, Hydrology | NONE | 2025-06-17 | SDPL/FY25-26/069 | 881738 | 1040450.84 | 881738 | 1040450.84 | 895103.4216 | 0 | 0 | 145347.4184 |  |  | 1 | 1 | 0 | Fully Billed |  | September |  | Closed
Erwin | WOCOMPANY_021 | SDPLDEAL-043 | One time Project |  | Completed | 2025-06-15 | 2025-04-10 | Purchase Order | 2025-06-16 | 2025-06-23 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-09-16 | SDPL/FY25-26/453 | 16648.2 | 19644.876 | 16648.2 | 19644.876 |  | 0 | 0 | 19644.876 |  |  | 50 HA |  | 50 | Fully Billed |  | September |  | Closed
Tanjiro | WOCOMPANY_005 | SDPLDEAL-044 | One time Project |  | Completed | 2025-07-02 | 2025-04-10 | LOA/LOI | 2025-06-14 | 2025-06-23 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-20 | SDPL/FY25-26/407 | 12774.7188 | 15074.1682 | 12774.7188 | 15074.1682 | 15074.6368 | 0 | 0 | -0.46862 |  |  | 57.55 HA |  | 57.55 | Fully Billed |  | August |  | Closed
Tanjiro | WOCOMPANY_051 | SDPLDEAL-046 | One time Project |  | Completed | 2025-05-05 | 2025-04-10 | Purchase Order | 2025-05-22 | 2025-06-22 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-25 | SDPL/FY25-26/369 | 390952.7636 | 461324.261 | 390887.404 | 461247.1367 | 461247.63 | 65.3596 | 77.1243 | -0.49328 |  | 2246.97 | 2186.54 HA |  | 2186.54 | Fully Billed |  | July |  | Closed
Tanjiro | WOCOMPANY_051 | SDPLDEAL-047 | One time Project |  | Completed | 2025-05-26 | 2025-04-10 | Purchase Order | 2025-05-15 | 2025-06-16 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-02 | SDPL/FY25-26/115 | 476539.31 | 562316.3858 | 469116.7409 | 553557.7542 | 506645.9025 | 7422.5691 | 8758.6316 | 46911.8517 |  | 1993.1968 | 2665 HA | 2623.49 | 41.51 | Fully Billed |  | July |  | Closed
Tanjiro | WOCOMPANY_051 | SDPLDEAL-048 | One time Project |  | Completed | 2025-05-13 | 2025-04-10 | Purchase Order | 2025-04-14 | 2025-06-30 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-06-27 | SDPL/FY25-26/097 | 145842.4865 | 172094.1341 | 145842.4865 | 172094.1341 | 157509.7547 | 0 | 0 | 14584.3794 |  | 815.61 | 815.6 HA | 815.61 | -0.01 | Fully Billed |  | July |  | Closed
Tanjiro | WOCOMPANY_051 | SDPLDEAL-049 | One time Project |  | Completed | 2025-06-10 | 2025-04-10 | Purchase Order | 2025-04-21 | 2025-07-21 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-22 | SDPL/FY25-26/363 | 707388.184 | 834718.0571 | 707388.184 | 834718.0571 | 763979.732 | 0 | 0 | 70738.3251 |  | 3961.22 | 3956HA | 3956 | 0 | Fully Billed |  | September |  | Closed
Timon | WOCOMPANY_046 | SDPLDEAL-050 | Proof of Concept |  | Completed |  | 2025-06-20 | Email Confirmation | 2025-06-23 | 2025-08-10 | OWNER_001 | Renewables | Videography for construction monitoring, Topography Survey: RGB | NONE |  |  | 1.2332 | 1.4552 |  | 0 |  | 1.2332 | 1.4552 | 0 |  |  | 2 location |  | 2 |  |  |  |  | Open
Alphonse | WOCOMPANY_009 | SDPLDEAL-051 | One time Project |  | Completed |  | 2025-06-17 | Purchase Order | 2025-01-01 | 2025-06-20 | OWNER_005 | Renewables | Others | SPECTRA | 2025-06-20 | SDPL/FY25-26/080 | 2466400 | 2910352 | 2466400 | 2910352 | 2910352 | 0 | 0 | 0 |  |  | 1 | 1 | 0 | Fully Billed |  |  |  | Closed
Mr. Krabs | WOCOMPANY_031 | SDPLDEAL-053 | Monthly Contract | May | Executed until current month |  | 2025-01-21 | Purchase Order | 2025-05-15 | 2025-05-19 | OWNER_004 | Mining | LiDAR Survey: LiDAR | SPECTRA | 2025-06-20 | SDPL/FY25-26/083 | 184980 | 218276.4 | 184980 | 218276.4 |  | 0 | 0 | 218276.4 |  |  | 7 mines | 1 | 6 | Fully Billed |  |  |  | Closed
Mojo Jojo | WOCOMPANY_036 | SDPLDEAL-054 | One time Project |  | Completed | 2025-01-23 | 2025-05-14 | Purchase Order | 2025-06-04 | 2025-06-11 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-31 | SDPL/FY25-26/377 | 65976.2 | 77851.916 | 65967.5676 | 77841.7298 | 77841.7298 | 8.6324 | 10.1862 | 0 |  |  | 194.52 Ha |  | 194.52 | Fully Billed |  | July |  | Closed
Asuna | WOCOMPANY_018 | SDPLDEAL-055 | Monthly Contract | May | Executed until current month |  | 2023-04-11 | Purchase Order |  |  | OWNER_001 | Mining | Videography for construction monitoring | NONE | 2025-03-31 | SDPL/FY24-25/565 | 1775808 | 2095453.44 | 369960 | 436552.8 | 224434.0389 | 1405848 | 1658900.64 | 212118.7611 |  |  | 24 Months |  | 24 | Partially Billed |  |  |  | Open
Sakura | WOCOMPANY_002 | SDPLDEAL-056 | One time Project |  | Completed |  | 2025-02-28 | Purchase Order | 2025-05-08 |  | OWNER_008 | Mining | Raw images/videography | NONE |  |  | 30830 | 36379.4 | 30830 | 36379.4 |  | 0 | 0 | 36379.4 |  |  | 73 Ha |  | 73 | Fully Billed |  |  |  | Closed
Asuna | WOCOMPANY_018 | SDPLDEAL-057 | Monthly Contract | May | Executed until current month |  | 2024-07-12 | Purchase Order |  |  | OWNER_001 | Mining | Videography for construction monitoring | NONE | 2025-03-31 | SDPL/FY24-25/566 | 665928 | 785795.04 | 110988 | 130965.84 | 81392.4332 | 554940 | 654829.2 | 49573.4068 |  |  | 18 Months |  | 18 | Partially Billed |  |  |  | Open
Gohan | WOCOMPANY_026 | SDPLDEAL-058 | One time Project |  | Completed |  | 2025-03-28 | Purchase Order |  |  | OWNER_001 | Construction | Topography Survey: RGB, Hydrology | DMO | 2025-07-18 | SDPL/FY25-26/358 | 1514246.28 | 1786810.6104 | 1514246.28 | 1786810.6104 | 1635385.9824 | 0 | 0 | 151424.628 |  |  | 1 | 1 | 0 | Fully Billed |  | August |  | Closed
Powerpuff Girls | WOCOMPANY_039 | SDPLDEAL-060 | Monthly Contract | Dec | Executed until current month |  | 2025-01-23 | Purchase Order |  |  | OWNER_001 | Mining | LiDAR Survey: LiDAR | NONE | 2025-06-16 | SDPL/FY25-26/412 | 3877242.46 | 4575146.1028 | 2684244.78 | 3167408.8404 | 2141430.8356 | 1192997.68 | 1407737.2624 | 1025978.0048 |  |  | 13 | 7 | 6 | Billed- Visit 7 |  |  |  | Open
Rafiki | WOCOMPANY_048 | SDPLDEAL-061 | Monthly Contract | June | Executed until current month |  | 2022-09-29 | Purchase Order |  |  | OWNER_003 | Mining | Topography Survey: RGB, Videography for construction monitoring | NONE |  |  | 2757435.2 | 3253773.536 |  | 0 |  | 2757435.2 | 3253773.536 | 0 |  |  | 5000 HA |  | 5000 | Fully Billed |  |  |  | Open
Bulbasaur | WOCOMPANY_050 | SDPLDEAL-062 | Annual Rate Contract | March | Executed until current month |  | 2025-03-25 | Purchase Order | 2025-02-05 | 2025-06-20 | OWNER_004 | Others | Others | SPECTRA + DMO |  |  | 158699.3858 | 187265.2752 |  | 0 |  | 158699.3858 | 187265.2752 | 0 |  |  | 98000 Acres |  | 98000 |  |  |  |  | Open
Alias_160 | WOCOMPANY_051 | SDPLDEAL-063 | Annual Rate Contract | May | Executed until current month |  | 2025-04-01 | LOA/LOI | 2025-04-01 | 2026-04-01 | OWNER_001 | Mining | Mine survey | NONE |  |  | 1.2332 | 1.4552 |  | 0 |  | 1.2332 | 1.4552 | 0 |  | 49.494 | NA | [6 empty] | Open
Shanks | WOCOMPANY_012 | SDPLDEAL-065 | One time Project |  | Completed |  | 2025-04-12 | Purchase Order | 2025-04-10 | 2025-04-16 | OWNER_004 | Renewables | Solar Inspection, Thermography | SPECTRA | 2025-06-24 | SDPL/FY25-26/088 | 24664 | 29103.52 | 24664 | 29103.52 | 2467.6332 | 0 | 0 | 26635.8868 | Priority |  | 40MW |  | 40 | Fully Billed |  |  |  | Closed
Subaru | WOCOMPANY_019 | SDPLDEAL-066 | One time Project |  | Completed |  | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-06-10 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-06-27 | SDPL/FY25-26/095 | 81555.2773 | 96235.2272 | 81555.2773 | 96235.2272 | 96235.2284 | 0 | 0 | -0.0012332 |  | 456.137 | 456.090 HA | 456.09 | 0 | Fully Billed |  | July |  | Closed
Frieza | WOCOMPANY_022 | SDPLDEAL-067 | One time Project |  | Completed |  | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-06-16 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-06 | SDPL/FY25-26/386 | 125169.8 | 147700.364 | 116542.0245 | 137519.5889 | 20977.4719 | 8627.7755 | 10180.7751 | 116542.117 |  | 467.87 | 700 HA | 651.75 | 48.25 | Fully Billed |  | July |  | Closed
Subaru | WOCOMPANY_019 | SDPLDEAL-068 | One time Project |  | Completed |  | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-06-16 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-21 | SDPL/FY25-26/361 | 61690.83 | 72795.1794 | 61690.83 | 72795.1794 | 72795.796 | 0 | 0 | -0.6166 |  | 353.851 | 345 HA | 345 | 0 | Fully Billed |  | July |  | Closed
Subaru | WOCOMPANY_019 | SDPLDEAL-069 | One time Project |  | Completed |  | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-06-16 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-11-03 | SDPL/FY25-26/528 | 144622.2968 | 170654.3102 | 144622.2968 | 170654.3102 |  | 0 | 0 | 170654.3102 |  | 918.667 | 808.790 HA |  | 808.79 | Fully Billed |  | November |  | Closed
Subaru | WOCOMPANY_019 | SDPLDEAL-070 | One time Project |  | Completed |  | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-06-17 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-28 | SDPL/FY25-26/375 | 80098.8064 | 94516.5916 | 80098.8064 | 94516.5916 | 73807.6366 | 0 | 0 | 20708.955 |  | 447.929 | 447.950 HA | 447.95 | 0 | Fully Billed |  | July |  | Closed
Subaru | WOCOMPANY_019 | SDPLDEAL-071 | One time Project |  | Completed |  | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-06-17 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-28 | SDPL/FY25-26/376 | 94747.9892 | 111802.6273 | 94747.9892 | 111802.6273 | 92852.5608 | 0 | 0 | 18950.0665 |  | 529.845 | 529.870 HA | 529.87 | 0 | Fully Billed |  | July |  | Closed
Subaru | WOCOMPANY_019 | SDPLDEAL-072 | One time Project |  | Completed |  | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-06-17 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-28 | SDPL/FY25-26/374 | 234398.0236 | 276589.6678 | 234398.0236 | 276589.6678 |  | 0 | 0 | 276589.6678 |  | 1310.802 | 1,310.850 | 1310.85 | -1309.85 | Fully Billed |  | July |  | Closed
Tanjiro | WOCOMPANY_051 | SDPLDEAL-073 | One time Project |  | Completed |  | 2025-04-28 | Purchase Order | 2025-05-15 | 2025-06-15 | OWNER_001 | Mining | Others | NONE | 2025-06-30 | SDPL/FY25-26/103 | 321865.2 | 379800.936 | 166482 | 196448.76 | 196448.76 | 155383.2 | 183352.176 | 0 |  |  | 145 pillars | 75 | 70 | Fully Billed |  | July |  | Closed
Frieza | WOCOMPANY_022 | SDPLDEAL-074 | One time Project |  | Completed |  | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-06-16 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-06-30 | SDPL/FY25-26/100 | 188717.7922 | 222686.9948 | 188717.7922 | 222686.9948 | 222687.5564 | 0 | 0 | -0.5616 |  | 1055.386 | 1100 HA | 1055.386 | 44.614 | Fully Billed |  | June |  | Closed
Yuji Itadori | WOCOMPANY_006 | SDPLDEAL-076 | One time Project |  | Completed |  | 2025-04-01 | Purchase Order | 2025-04-05 | 2025-04-11 | OWNER_003 | Renewables | Hydrology, Topography Survey: RGB | NONE |  |  | 431620 | 509311.6 | 431620 | 509311.6 | 509311.6 | 0 | 0 | 0 |  |  | 222 HA |  | 222 | [7 empty] | BIlled
Winnie the Pooh | WOCOMPANY_042 | SDPLDEAL-077 | Proof of Concept |  | Completed |  | 2025-04-18 | Email Confirmation | 2025-04-30 | 2025-04-30 | OWNER_003 | Mining | Volumetric survey, Others | NONE |  |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  |  | 152 HA |  | 152 | [7 empty] | Not Billable
Alias_162 | WOCOMPANY_052 | SDPLDEAL-078 | Proof of Concept |  | Completed |  | 2025-06-06 | Email Confirmation | 2025-06-13 | 2025-06-13 | OWNER_003 | Mining | Volumetric survey | NONE |  |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  |  | NA | [9 empty] | Not Billable
Trunks | WOCOMPANY_015 | SDPLDEAL-079 | Proof of Concept |  | Completed |  | 2025-07-01 | Email Confirmation | 2025-04-23 | 2025-04-23 | OWNER_003 | Railways | Road/rail survey | NONE |  |  | 554940 | 654829.2 |  | 0 |  | 554940 | 654829.2 | 0 |  |  | NA | [9 empty] | Not Billable
Tuxedo Mask | WOCOMPANY_052 | SDPLDEAL-080 | Annual Rate Contract | Dec | Executed until current month |  | 2025-04-01 | Purchase Order | 2025-04-01 | 2028-03-31 | OWNER_003 | Mining | Topography Survey: RGB, Volumetric survey | NONE | 2025-07-03 | SDPL/FY25-26/118 | 2959680 | 3492422.4 | 493282.4664 | 582073.3104 |  | 2466397.5336 | 2910349.0896 | 582073.3104 | Priority |  | 36 AU | 3 | 33 | Billed- Visit 3 |  |  |  | Open
Timon | WOCOMPANY_046 | SDPLDEAL-081 | Proof of Concept |  | Completed |  | 2025-06-27 | Purchase Order | 2025-07-01 | 2025-08-17 | OWNER_001 | Renewables | Topography Survey: RGB, Raw images/videography | SPECTRA | 2025-11-03 |  | 277470 | 327414.6 | 277470 | 327414.6 |  | 0 | 0 | 327414.6 |  |  | 45days |  | 45 | Fully Billed |  | Dec |  | Closed
Timon | WOCOMPANY_046 | SDPLDEAL-082 | Proof of Concept |  | Pause / struck |  | 2025-06-19 | Purchase Order | 2025-07-01 | 2025-08-17 | OWNER_001 | Renewables | Topography Survey: RGB, Raw images/videography, Others | SPECTRA | 2025-11-03 |  | 277470 | 327414.6 | 277470 | 327414.6 |  | 0 | 0 | 327414.6 |  |  | 45 days |  | 45 | Fully Billed |  |  |  | Closed
Subaru | WOCOMPANY_019 | SDPLDEAL-083 | One time Project |  | Completed |  | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-06-25 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-02 | SDPL/FY25-26/114 | 143051.2 | 168800.416 | 130176.592 | 153608.3786 | 26035.3184 | 12874.608 | 15192.0374 | 127573.0602 |  | 726.976 | 800 |  | 800 | Fully Billed |  | July |  | Closed
Tuxedo Mask | WOCOMPANY_041 | SDPLDEAL-084 | One time Project |  | Completed |  | 2025-06-21 | Purchase Order | 2025-07-01 | 2025-07-10 | OWNER_003 | Renewables | Others | NONE | 2025-07-04 | SDPL/FY25-26/120 | 215810 | 254655.8 | 215810 | 254655.8 |  | 0 | 0 | 254655.8 | Priority |  | 1 | 1 | 0 | Fully Billed |  |  |  | Closed
Luffy | WOCOMPANY_032 | SDPLDEAL-085 | One time Project |  | Completed |  | 2025-06-21 | LOA/LOI | 2025-06-01 | 2025-06-30 | OWNER_003 | Renewables | Thermography | NONE |  |  | #VALUE! | 0 |  | 0 |  | 0 | 0 | 0 |  |  | 1 |  | 1 |  |  |  |  | Open |  |  | Update Required
Alias_162 | WOCOMPANY_052 | SDPLDEAL-086 | Annual Rate Contract |  | Completed |  | 2024-07-22 | Purchase Order | 2024-07-30 | 2025-07-30 | OWNER_001 | Mining | Volumetric survey | NONE |  |  | 710616.2083 | 838527.1258 | 710616.2083 | 838527.1258 | 767463.522 | 0 | 0 | 71063.6038 | Priority |  | 8 units |  | 8 | Fully Billed |  |  |  | Closed
Alias_162 | WOCOMPANY_052 | SDPLDEAL-087 | Annual Rate Contract | Dec | Executed until current month |  | 2025-08-08 | Purchase Order | 2025-04-01 | 2026-03-31 | OWNER_001 | Mining | Volumetric survey | NONE | 2025-12-09 | SDPL/FY25-26/572 | 1065928.752 | 1257795.9274 | 838526.672 | 989461.473 | 618232.7568 | 227402.08 | 268334.4544 | 371228.7162 |  |  | 12 months |  | 12 | Fully Billed
Mojo Jojo | WOCOMPANY_036 | SDPLDEAL-088 | One time Project |  | Completed |  | 2025-04-26 | Purchase Order | 2025-04-28 | 2025-08-15 | OWNER_001 | Mining | Topography Survey: RGB | SPECTRA | 2025-09-03 | SDPL/FY25-26/419 | 154150 | 181897 | 154150 | 181897 | 166482 | 0 | 0 | 15415 |  |  | 200 Acres |  | 200 | Fully Billed |  | September |  | Closed
Obito | WOCOMPANY_023 | SDPLDEAL-089 | Annual Rate Contract |  | Completed |  | 2025-07-09 | LOA/LOI | 2025-06-21 | 2026-06-20 | OWNER_003 | Mining | Others | NONE |  |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  |  | 1 |  | 1 | [7 empty] | Not Billable
Mojo Jojo | WOCOMPANY_036 | SDPLDEAL-090 | One time Project |  | Completed |  | 2025-04-15 | Purchase Order | 2025-05-12 | 2025-06-20 | OWNER_001 | Mining | Topography Survey: RGB | SPECTRA | 2025-08-06 | SDPL/FY25-26/387 | 223971.3176 | 264286.1548 | 223971.3176 | 264286.1548 | 264287.092 | 0 | 0 | -0.93723 |  | 609.44 | 660.43HA | 660.43 | 0 | Fully Billed |  | August |  | Closed
Rafiki | WOCOMPANY_048 | SDPLDEAL-091 | Proof of Concept |  | Completed |  | 2025-07-08 | Email Confirmation | 2025-06-11 | 2025-06-19 | OWNER_003 | Mining | Thermography | NONE |  |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  |  | 3 Rooftops |  | 3 | [7 empty] | Not Billable
Alias_160 | WOCOMPANY_051 | SDPLDEAL-092 | One time Project |  | Completed |  | 2025-04-10 | Purchase Order | 2025-05-01 | 2025-06-25 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-08-06 | SDPL/FY25-26/390 | 357628 | 422001.04 | 321686.386 | 379589.9355 | 347420.6186 | 35941.614 | 42411.1045 | 32169.3169 |  | 2173.17 | 2000 |  | 2000 | Fully Billed |  | August |  | Closed
Obito | WOCOMPANY_023 | SDPLDEAL-093 | One time Project |  | Completed |  | 2025-07-15 | LOA/LOI | 2025-07-21 | 2025-07-25 | OWNER_003 | Mining | Others | NONE |  |  | 76458.4 | 90220.912 |  | 0 |  | 76458.4 | 90220.912 | 0 |  |  | 1 |  | 1 | [7 empty] | Update Required
GG go | WOCOMPANY_035 | SDPLDEAL-094 | One time Project |  | Completed |  | 2025-07-10 | Purchase Order | 2025-07-15 | 2025-07-31 | OWNER_003 | Renewables | Hydrology | NONE |  |  | 749785.6 | 884747.008 |  | 0 |  | 749785.6 | 884747.008 | 0 |  |  | 1415 Acres |  | 1415 | [7 empty] | Update Required
Subaru | WOCOMPANY_019 | SDPLDEAL-095 | One time Project |  | Completed |  | 2025-07-17 | Purchase Order | 2025-05-01 | 2025-05-30 | OWNER_001 | Mining | Topography Survey: RGB | NONE | 2025-07-28 | SDPL/FY25-26/373 | 155665.6028 | 183685.4113 | 155665.6028 | 183685.4113 | 3115.0632 | 0 | 0 | 180570.3481 |  | 813.635 | 870.45 HA |  | 870.45 | Fully Billed |  | July |  | Closed
Alphonse | WOCOMPANY_009 | SDPLDEAL-096 | One time Project |  | Completed |  | 2025-07-16 | Purchase Order | 2025-07-14 | 2025-07-28 | OWNER_001 | Renewables | Topography Survey: RGB | NONE | 2025-08-20 | SDPL/FY25-26/413 | 986560 | 1164140.8 | 986560 | 1164140.8 |  | 0 | 0 | 1164140.8 |  |  | 4 Sites |  | 4 | Fully Billed |  | September |  | Closed
Alias_160 | WOCOMPANY_051 | SDPLDEAL-097 | One time Project |  | Completed |  | 2025-04-10 |  | 2025-05-01 | 2025-05-31 | OWNER_001 | Mining | Topography Survey: RGB | SPECTRA | 2025-07-25 | SDPL/FY25-26/370 | 84190.564 | 99344.8655 | 79060.452 | 93291.3334 | 85383.907 | 5130.112 | 6053.5322 | 7907.4264 |  | 442.14 | 446 HA |  | 446 | Fully Billed |  | July |  | Closed
Erwin | WOCOMPANY_021 | SDPLDEAL-098 | One time Project |  | Completed |  | 2025-05-22 | Purchase Order | 2025-05-26 | 2025-06-25 | OWNER_001 | Mining | Topography Survey: RGB | SPECTRA | 2025-08-20 | SDPL/FY25-26/405 | 319811.922 | 377378.068 | 319811.922 | 377378.068 |  | 0 | 0 | 377378.068 |  |  | 960.5 HA |  | 960.5 | Fully Billed |  | August |  | Closed
Goku | WOCOMPANY_003 | SDPLDEAL-099 | One time Project |  | Ongoing |  | 2025-07-23 | Purchase Order | 2025-07-28 | 2025-09-30 | OWNER_003 | Railways | LiDAR Survey: LiDAR, Road/rail survey | NONE | 2025-09-01 | SDPL/FY25-26/424 | 14391444 | 16981903.92 | 246640 | 291035.2 | 291035.2 | 14144804 | 16690868.72 | 0 |  |  | 778 |  | 778 | [7 empty] | Partially Billed
Erwin | WOCOMPANY_021 | SDPLDEAL-100 | Annual Rate Contract |  | Completed |  | 2025-05-28 | Purchase Order | 2025-07-01 | 2025-07-15 | OWNER_001 | Mining | Volumetric survey | SPECTRA | 2025-08-20 | SDPL/FY25-26/406 | 791874.716 | 934412.1649 | 594265.4161 | 701233.191 |  | 197609.2999 | 233178.9738 | 701233.191 |  |  | 2379.7 HA |  | 2379.7 | Fully Billed |  | Dec |  | Open
Nami | WOCOMPANY_002 | SDPLDEAL-102 | One time Project |  | Completed |  | 2025-08-02 | Purchase Order | 2025-08-04 | 2025-08-09 | OWNER_003 | Mining | Raw images/videography | NONE |  |  | 64373.04 | 75960.1872 |  | 0 |  | 64373.04 | 75960.1872 | 0 |  |  | 1 |  | 1 | [7 empty] | Update Required
Ben Tennyson | WOCOMPANY_033 | SDPLDEAL-103 | One time Project |  | Completed |  | 2025-08-01 | Purchase Order | 2025-07-01 | 2025-07-31 | OWNER_003 | Renewables | Hydrology, Topography Survey: RGB | NONE |  |  | 487114 | 574794.52 |  | 0 |  | 487114 | 574794.52 | 0 |  |  | 1 |  | 1 | [7 empty] | Update Required
Subaru | WOCOMPANY_019 | SDPLDEAL-105 | One time Project |  | Completed |  | 2025-08-06 | Purchase Order | 2025-05-01 | 2025-05-29 | OWNER_001 | Mining | Topography Survey: RGB | SPECTRA | 2025-08-06 | 2025-08-06 | 20563.61 | 24265.0598 | 20251.6104 | 23896.9003 | 23896.9496 | 311.9996 | 368.1595 | -0.049328 |  |  | 115HA |  | 115 | Fully Billed |  | August |  | Closed
Yuji Itadori | WOCOMPANY_006 | SDPLDEAL-106 | One time Project |  | Completed |  | 2025-08-08 | Purchase Order | 2025-08-08 | 2025-08-20 | OWNER_003 | Renewables | Hydrology, Topography Survey: RGB | NONE | 2025-09-12 | SDPL/FY25-26/442 | 339130 | 400173.4 | 339130 | 400173.4 | 400173.4 | 0 | 0 | 0 |  |  | 1 |  | 1 | Fully Billed
Alphonse | WOCOMPANY_009 | SDPLDEAL-108 | One time Project |  | Completed |  | 2025-08-18 | Purchase Order | 2025-08-14 | 2025-08-30 | OWNER_001 | Renewables | Topography Survey: RGB, Hydrology | SPECTRA | 2025-09-24 | SDPL/FY25-26/476 | 477247.7957 | 563152.399 | 477247.7957 | 563152.399 | 563151.8788 | 0 | 0 | 0.52016 |  |  | 537 Acres |  | 537 | Fully Billed |  | November |  | Closed
Rafiki | WOCOMPANY_048 | SDPLDEAL-109 | Annual Rate Contract |  | Ongoing |  | 2025-08-11 | Purchase Order | 2025-09-01 | 2027-08-31 | OWNER_003 | Renewables | Topography Survey: RGB, Thermography | NONE |  |  | 616600 | 727588 |  | 0 |  | 616600 | 727588 | 0 |  |  | 1 |  | 1 | [7 empty] | Update Required
Alias_162 | WOCOMPANY_052 | SDPLDEAL-111 |  |  |  |  | 2024-11-22 |  |  |  |  | Mining | Others | DMO |  |  | 863240 | 1018623.2 | 739920 | 873105.6 | 864473.2 | 123320 | 145517.6 | 8632.4
Ben Tennyson | WOCOMPANY_034 | SDPLDEAL-112 |  |  | Completed |  | 2024-05-16 |  |  |  |  | Renewables | Topography Survey: RGB, Hydrology |  |  |  | 215810 | 254655.8 | 215810 | 254655.8 | 254655.8 | 0 | 0 | 0
Alphonse | WOCOMPANY_009 | SDPLDEAL-113 |  |  |  |  | 2024-12-20 |  |  |  | OWNER_001 | Renewables | Topography Survey: RGB, Hydrology |  |  |  | 607351 | 716674.18 | 607351 | 716674.18 | 716674.18 | 0 | 0 | 0
Yuji Itadori | WOCOMPANY_006 | SDPLDEAL-115 |  |  | Completed |  | 2025-03-24 |  |  |  |  | Renewables | Hydrology |  |  |  | 616600 | 727588 | 616600 | 727588 | 727588 | 0 | 0 | 0 | [5 empty] | Fully Billed
Ace | WOCOMPANY_013 | SDPLDEAL-116 |  |  | Completed |  | 2025-03-05 |  |  |  |  | Others | Topography Survey: RGB |  |  |  | 176347.6 | 208090.168 | 176347.6 | 208090.168 |  | 0 | 0 | 208090.168 | [5 empty] | Fully Billed
Shanks | WOCOMPANY_012 | SDPLDEAL-117 |  |  | Completed |  | 2025-03-31 |  |  |  |  | Renewables | Thermography |  |  |  | 221636.87 | 261531.5066 | 221636.87 | 261531.5066 |  | 0 | 0 | 261531.5066 | [5 empty] | Fully Billed
Bulbasaur | WOCOMPANY_050 | SDPLDEAL-118 |  |  | Completed |  | 2025-03-25 |  |  |  |  | Renewables | Topography Survey: RGB |  |  |  | 308300 | 363794 | 308300 | 363794 |  | 0 | 0 | 363794 | [5 empty] | Fully Billed
Sesshomaru | WOCOMPANY_017 | SDPLDEAL-119 |  |  | Completed |  | 2024-12-03 |  |  |  |  | Renewables | Hydrology, Topography Survey: RGB |  | 2025-04-16 | SDPL/FY25-26/002 | 446418.4 | 526773.712 | 446418.4 | 526773.712 | 526773.712 | 0 | 0 | 0 | [5 empty] | Fully Billed |  |  |  | Closed
Mr. Krabs | WOCOMPANY_031 | SDPLDEAL-120 |  |  | Completed |  | 2025-01-21 |  |  |  |  | Mining | Volumetric survey |  | 2025-06-20 | SDPL/FY25-26/083 | 554940 | 654829.2 | 554940 | 654829.2 | 588236.4 | 0 | 0 | 66592.8 | [5 empty] | Fully Billed |  |  |  | Closed
Pumbaa | WOCOMPANY_047 | SDPLDEAL-121 | Annual Rate Contract |  | Ongoing |  | 2025-09-02 | LOA/LOI | 2025-09-02 | 2026-09-02 | OWNER_004 | Renewables | Thermography | SPECTRA |  |  | 5224698.44 | 6165144.1592 | 2330748 | 2750282.64 |  | 2893950.44 | 3414861.5192 | 2750282.64 |  |  | Rate based on MW slabs |  |  | Partially Billed |  |  |  | Open |  |  | Partially Billed
Stitch | WOCOMPANY_044 | SDPLDEAL-122 |  |  | Completed |  | 2025-04-01 |  |  |  |  | Renewables | Flood Risk |  | 2025-04-29 | SDPL/FY25-26/009 | 431620 | 509311.6 | 431620 | 509311.6 | 509311.6 | 0 | 0 | 0 | [5 empty] | Fully Billed |  |  |  | Closed
Sasuke | WOCOMPANY_002 | SDPLDEAL-123 |  |  | Completed |  | 2024-12-25 |  |  |  |  | Mining | LiDAR Survey: LiDAR |  |  |  | 371193.2 | 438007.976 | 371193.2 | 438007.976 |  | 0 | 0 | 438007.976 | [5 empty] | Fully Billed |  |  |  | Closed
Alphonse | WOCOMPANY_009 | SDPLDEAL-124 |  |  |  |  | 2025-07-24 |  |  |  |  | Renewables | Others |  | 2025-07-31 | SDPL/FY25-26/378 | 24664 | 29103.52 | 24664 | 29103.52 |  | 0 | 0 | 29103.52 | [5 empty] | Fully Billed |  |  |  | Closed
Timon | WOCOMPANY_046 | SDPLDEAL-125 | Proof of Concept |  | Completed |  | 2025-09-08 | Purchase Order | 2025-09-11 | 2025-10-26 | OWNER_001 | Renewables | Others | SPECTRA |  |  | 277470 | 327414.6 | 277470 | 327414.6 |  | 0 | 0 | 327414.6 |  |  | 45days |  | 45 | Fully Billed |  | Dec
Gohan | WOCOMPANY_026 | SDPLDEAL-126 | One time Project |  | Completed |  | 2025-09-10 | Purchase Order | 2025-08-01 | 2025-09-05 | OWNER_001 | Construction | Topography Survey: RGB | NONE | 2025-09-15 | SDPL/FY25-26/448 | 788298.436 | 930192.1545 | 788298.436 | 930192.1545 | 914425.1992 | 0 | 0 | 15766.9553 |  |  | 1 |  | 1 | Fully Billed |  | October |  | Closed
Kaguya | WOCOMPANY_014 | SDPLDEAL-127 | One time Project |  | Completed |  | 2025-09-12 | Purchase Order | 2025-09-15 | 2025-10-31 | OWNER_003 | Railways | Others | NONE |  |  | 5061052.8 | 5972042.304 |  | 0 |  | 5061052.8 | 5972042.304 | 0 |  |  | 304 RKM |  | 304
Bugs Bunny | WOCOMPANY_028 | SDPLDEAL-128 | One time Project |  | Ongoing |  | 2025-09-12 | Purchase Order | 2025-09-15 | 2025-10-31 | OWNER_003 | Railways | Others | NONE |  |  | 8789158.7113 | 10371207.2793 |  | 0 |  | 8789158.7113 | 10371207.2793 | 0 |  |  | 580 RKM |  | 580
Armin | WOCOMPANY_020 | SDPLDEAL-129 | Annual Rate Contract |  | Completed | 2025-09-20 | 2025-09-10 | Purchase Order | 2025-07-24 | 2025-12-31 | OWNER_001 | Mining | Topography Survey: RGB | SPECTRA |  |  | 218478.6448 | 257804.8009 | 145653.4986 | 171871.1284 |  | 72825.1462 | 85933.6725 | 171871.1284 |  |  | 3 Quarter (Till Dec) |  | 3 | Fully Billed |  | October |  | Closed
Armin | WOCOMPANY_020 | SDPLDEAL-130 | Annual Rate Contract |  | Completed | 2025-09-20 | 2025-09-11 | Purchase Order | 2025-07-24 | 2025-12-31 | OWNER_001 | Mining | Topography Survey: RGB | SPECTRA |  |  | 484453.9876 | 571655.7054 | 322971.0351 | 381105.8214 |  | 161482.9525 | 190549.8839 | 381105.8214 |  |  | 3 Quarter (till December 2025) |  | 3 | Fully Billed |  | Dec |  | Closed
Sakura | WOCOMPANY_002 | SDPLDEAL-131 | One time Project |  | Pause / struck |  | 2025-09-17 | Purchase Order | 2025-09-15 | 2025-10-15 | OWNER_003 | Mining | LiDAR Survey: LiDAR | NONE |  |  | 1224740.248 | 1445193.4926 |  | 0 |  | 1224740.248 | 1445193.4926 | 0 |  |  | 1 |  | 1 | [7 empty] | Stuck
Sakura | WOCOMPANY_002 | SDPLDEAL-132 | One time Project |  | Pause / struck |  | 2025-09-17 | Purchase Order | 2025-09-15 | 2025-10-15 | OWNER_003 | Mining | LiDAR Survey: LiDAR | NONE |  |  | 1219634.8 | 1439169.064 |  | 0 |  | 1219634.8 | 1439169.064 | 0 |  |  | 1 |  | 1 | [7 empty] | Stuck
Gojo | WOCOMPANY_005 | SDPLDEAL-134 | One time Project |  | Completed |  | 2025-09-20 | Purchase Order | 2025-09-27 | 2025-10-15 | OWNER_001 | Mining | Topography Survey: RGB, Mine survey | NONE |  | SDPL/FY25-26/558 | 192009.24 | 226570.9032 | 58823.64 | 69411.8952 |  | 133185.6 | 157159.008 | 69411.8952 |  |  | 865 |  | 865 | Partially Billed |  |  |  | Open
Faye Valentine | WOCOMPANY_010 | SDPLDEAL-133 | One time Project |  | Completed |  | 2024-07-19 | Purchase Order | 2025-09-11 | 2025-09-19 | OWNER_003 | Renewables | Solar Inspection | NONE |  |  | 57487090.4901 | 67834766.7784 | 57487090.4901 | 67834766.7784 | 57487090.4901 | 0 | 0 | 10347676.2882 |  |  | NA |  |  | Fully Billed | [6 empty] | BIlled
Alias_160 | WOCOMPANY_051 | SDPLDEAL-135 | One time Project |  | Completed |  | 2025-07-25 | Purchase Order | 2025-05-01 | 2025-05-27 | OWNER_001 | Mining | Mine survey, Topography Survey: RGB | SPECTRA | 2025-10-07 | SDPL/FY25-26/484 | 89407 | 105500.26 | 89407 | 105500.26 | 104886.6197 | 0 | 0 | 613.6403 |  |  | 500 |  | 500 | Fully Billed |  | October |  | Closed
Scooby-Doo | WOCOMPANY_002 | SDPLDEAL-136 | One time Project |  | Ongoing |  | 2025-09-27 | Purchase Order | 2025-09-29 | 2025-10-10 | OWNER_003 | Mining | Others | NONE |  |  | 143051.2 | 168800.416 |  | 0 |  | 143051.2 | 168800.416 | 0 |  |  | 1 |  | 1
Scooby-Doo | WOCOMPANY_002 | SDPLDEAL-137 | One time Project |  | Ongoing |  | 2025-09-27 | Purchase Order | 2025-09-29 | 2025-10-30 | OWNER_003 | Mining | Others | NONE |  |  | 143051.2 | 168800.416 |  | 0 |  | 143051.2 | 168800.416 | 0 |  |  | 1 |  | 1
Alias_160 | WOCOMPANY_051 | SDPLDEAL-138 | One time Project |  | Pause / struck |  | 2025-09-19 | Purchase Order | 2025-10-06 | 2025-10-30 | OWNER_001 | Mining | Topography Survey: RGB | SPECTRA |  |  | 261901.7132 | 309044.0216 |  | 0 |  | 261901.7132 | 309044.0216 | 0 |  |  | 1464.66 HA |  | 1464.66 | Not billed yet
Scooby-Doo | WOCOMPANY_002 | SDPLDEAL-139 | One time Project |  | Ongoing |  | 2025-10-03 | Purchase Order | 2025-09-20 | 2025-10-20 | OWNER_003 | Mining | LiDAR Survey: LiDAR | NONE |  |  | 699730.012 | 825681.4142 |  | 0 |  | 699730.012 | 825681.4142 | 0 |  |  | 1 |  | 1
Trunks | WOCOMPANY_015 | SDPLDEAL-140 | One time Project |  | Ongoing |  | 2025-10-08 | Purchase Order | 2025-09-29 | 2025-10-31 | OWNER_003 | Railways | LiDAR Survey: LiDAR | NONE |  |  | 3237150 | 3819837 |  | 0 |  | 3237150 | 3819837 | 0 |  |  | 350 KM |  | 350
Scooby-Doo | WOCOMPANY_002 | SDPLDEAL-141 | One time Project |  | Not Started |  | 2025-10-09 | Purchase Order | 2025-09-30 | 2025-10-30 | OWNER_003 | Mining | LiDAR Survey: LiDAR | NONE |  |  | 383192.236 | 452166.8385 |  | 0 |  | 383192.236 | 452166.8385 | 0 |  |  | 1 |  | 1
Inuyasha | WOCOMPANY_016 | SDPLDEAL-142 | One time Project |  | Completed | 2026-01-08 | 2025-10-14 | Purchase Order | 2025-10-17 | 2025-11-10 | OWNER_003 | Renewables | Topography Survey: RGB, Hydrology, Flood Risk | NONE |  |  | 419288 | 494759.84 |  | 0 |  | 419288 | 494759.84 | 0 |  |  | 1 |  | 1 | Stuck
Patrick Star | WOCOMPANY_030 | SDPLDEAL-143 | One time Project |  | Completed | 2025-11-05 | 2025-10-16 | Purchase Order | 2025-10-08 | 2025-10-16 | OWNER_001 | Others | Hydrology | NONE |  |  | 246640 | 291035.2 | 246640 | 291035.2 |  | 0 | 0 | 291035.2 |  |  | 10 ha |  | 10 | Fully Billed |  | Dec
Kaguya | WOCOMPANY_014 | SDPLDEAL-144 | One time Project |  | Ongoing |  | 2025-10-27 | Purchase Order | 2025-11-03 | 2025-12-01 | OWNER_003 | Railways | Road/rail survey, LiDAR Survey: LiDAR | NONE |  |  | 4628199.6 | 5461275.528 |  | 0 |  | 4628199.6 | 5461275.528 | 0 |  |  | 278 |  | 278
Sakura | WOCOMPANY_002 | SDPLDEAL-145 | One time Project |  | Not Started |  | 2025-10-27 | Purchase Order | 2025-10-27 | 2025-11-03 | OWNER_003 | Mining | Raw images/videography | NONE |  |  | 64373.04 | 75960.1872 |  | 0 |  | 64373.04 | 75960.1872 | 0 |  |  | 1 |  | 1
Scooby-Doo | WOCOMPANY_002 | SDPLDEAL-146 | One time Project |  | Ongoing |  | 2025-10-27 | Purchase Order | 2025-10-27 | 2025-11-03 | OWNER_003 | Mining | LiDAR Survey: LiDAR, Mine survey | NONE |  |  | 679308.22 | 801583.6996 |  | 0 |  | 679308.22 | 801583.6996 | 0 |  |  | 1 |  | 1
Katara | WOCOMPANY_037 | SDPLDEAL-147 | One time Project |  | Partial Completed | 2025-12-18 | 2025-10-28 | Purchase Order | 2025-11-03 | 2025-11-11 | OWNER_003 | Railways | LiDAR Survey: LiDAR, Road/rail survey, Others | NONE |  |  | 1850391.936 | 2183462.4845 |  | 0 |  | 1850391.936 | 2183462.4845 | 0 |  |  | NA . Verbal confirmation for 59 km | [9 empty] | Stuck
Sakura | WOCOMPANY_002 | SDPLDEAL-149 | Monthly Contract |  | Ongoing |  | 2025-10-30 | Purchase Order | 2025-11-01 | 2026-04-01 | OWNER_003 | Renewables | Others | SPECTRA |  |  | 6011850 | 7093983 |  | 0 |  | 6011850 | 7093983 | 0 |  |  | 4,875,000.000 |  | 4
Dolphin | WOCOMPANY_029 | SDPLDEAL-150 | One time Project |  | Ongoing |  | 2025-08-12 | LOA/LOI | 2025-08-20 | 2025-12-16 | OWNER_002 | Powerline | LiDAR Survey: LiDAR | NONE |  |  | 5026523.2 | 5931297.376 |  | 0 |  | 5026523.2 | 5931297.376 | 0 |  |  | 1250 towers |  | 1250
Yuji Itadori | WOCOMPANY_006 | SDPLDEAL-151 | One time Project |  | Completed | 2025-12-17 | 2025-11-06 | Purchase Order | 2025-11-10 | 2025-12-01 | OWNER_003 | Renewables | Hydrology, Topography Survey: RGB | NONE |  | SDPL/FY25-26/442 | 339130 | 400173.4 | 339130 | 400173.4 | 400173.4 | 0 | 0 | 0 |  |  | 1 |  | 1 | [7 empty] | Update Required
Ben Tennyson | WOCOMPANY_033 | SDPLDEAL-152 | One time Project |  | Completed | 2026-01-09 | 2025-11-04 | Email Confirmation | 2025-11-07 | 2025-11-28 | OWNER_003 | Renewables | Topography Survey: RGB, Hydrology | NONE |  |  | 295968 | 349242.24 |  | 0 |  | 295968 | 349242.24 | 0 |  |  | 1 |  | 1 | [7 empty] | Update Required
Megumi | WOCOMPANY_007 | SDPLDEAL-153 | One time Project |  | Completed |  | 2025-04-01 | Purchase Order | 2025-04-01 | 2025-04-10 | OWNER_003 | Renewables | Others | NONE | 2025-03-31 | SDPL/FY24-25/577 | 365779.452 | 431619.7534 | 365779.452 | 431619.7534 | 431620 | 0 | 0 | -0.24664 |  |  | 1 |  | 1 | Fully Billed |  |  |  | Closed
Donkey | WOCOMPANY_040 | SDPLDEAL-154 | One time Project |  | Ongoing |  | 2025-11-10 | Purchase Order | 2025-11-13 | 2025-12-31 | OWNER_003 | Railways | LiDAR Survey: LiDAR, Road/rail survey, Raw images/videography | NONE |  |  | 1346654.4 | 1589052.192 |  | 0 |  | 1346654.4 | 1589052.192 | 0 |  |  | 104 km |  | 104
Donkey | WOCOMPANY_040 | SDPLDEAL-155 | One time Project |  | Ongoing |  | 2025-11-12 | Purchase Order | 2025-11-13 | 2026-01-31 | OWNER_003 | Railways | LiDAR Survey: LiDAR, Road/rail survey | NONE |  |  | 9089917.2 | 10726102.296 |  | 0 |  | 9089917.2 | 10726102.296 | 0 |  |  | 702 |  | 702
Golden fish | WOCOMPANY_027 | SDPLDEAL-156 | Proof of Concept |  | Not Started |  | 2025-10-16 | LOA/LOI | 2025-12-01 | 2025-12-31 | OWNER_006 | Mining | LiDAR Survey: LiDAR, Volumetric survey | SPECTRA |  |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  |  |  | Open |  |  | Not Billable
Alphonse | WOCOMPANY_009 | SDPLDEAL-157 | One time Project |  |  |  | 2025-11-14 | Purchase Order | 2025-11-14 | 2025-11-14 | OWNER_005 | Renewables | Others | SPECTRA | 2025-11-19 | SDPL/FY25-26/549 | 277470 | 327414.6 | 277470 | 327414.6 | 321865.2 | 0 | 0 | 5549.4 |  |  | 3 subscriptions |  | 3 | Partially Billed
Alphonse | WOCOMPANY_009 | SDPLDEAL-158 | One time Project |  | Completed | 2025-11-01 | 2025-10-23 | Purchase Order | 2025-10-16 | 2025-10-31 | OWNER_001 | Renewables | Hydrology, Topography Survey: RGB | NONE | 2025-11-21 | SDPL/FY25-26/554 | 477248.4 | 563153.112 | 477248.4 | 563153.112 | 515428.272 | 0 | 0 | 47724.84 |  |  | 220HA |  | 220 | Fully Billed |  | November |  | Closed
Timon | WOCOMPANY_046 | SDPLDEAL-159 | One time Project |  | Completed | 2025-12-05 | 2025-11-08 | Purchase Order | 2025-11-03 | 2025-12-20 | OWNER_001 | Renewables | Others | SPECTRA |  |  | 277470 | 327414.6 | 277470 | 327414.6 |  | 0 | 0 | 327414.6 |  |  | 45days |  | 45 | Fully Billed |  | Dec
Timon | WOCOMPANY_046 | SDPLDEAL-160 | One time Project |  | Completed | 2025-12-04 | 2025-11-08 | Purchase Order | 2025-11-03 | 2025-12-20 | OWNER_001 | Renewables | Powerline Inspection, Videography for construction monitoring, Others | SPECTRA |  |  | 277470 | 327414.6 | 277470 | 327414.6 |  | 0 | 0 | 327414.6 |  |  | 45 days |  | 45 | Not billed yet
Scooby-Doo | WOCOMPANY_002 | SDPLDEAL-161 | One time Project |  | Completed | 2026-01-08 | 2025-11-21 | Purchase Order | 2025-11-20 | 2025-11-30 | OWNER_003 | Mining | LiDAR Survey: LiDAR | NONE |  |  | 304452.416 | 359253.8509 |  | 0 |  | 304452.416 | 359253.8509 | 0 |  |  | 1 |  | 1 | [7 empty] | Update Required
Whis | WOCOMPANY_025 | SDPLDEAL-162 | One time Project |  | Partial Completed | 2026-01-09 | 2025-12-01 | Purchase Order | 2025-12-01 | 2025-12-31 | OWNER_003 | Railways | LiDAR Survey: LiDAR | NONE |  |  | 924900 | 1091382 |  | 0 |  | 924900 | 1091382 | 0 |  |  | 1 |  | 1
Rengoku | WOCOMPANY_002 | SDPLDEAL-163 | One time Project |  | Not Started |  | 2025-12-01 | Purchase Order | 2025-12-01 | 2025-12-31 | OWNER_003 | Mining | Topography Survey: RGB, LiDAR Survey: LiDAR | NONE |  |  | 141818 | 167345.24 |  | 0 |  | 141818 | 167345.24 | 0 |  |  | 1 |  | 1
Alphonse | WOCOMPANY_009 | SDPLDEAL-164 | One time Project |  | Completed | 2025-11-28 | 2025-11-27 | Purchase Order | 2025-11-27 | 2025-12-23 | OWNER_001 | Renewables | Topography Survey: RGB | SPECTRA | 2025-12-19 | SDPL/FY25-26/894 | 511777.963 | 603897.9963 | 511778.0123 | 603898.0546 | 552719.0068 | -0.049328 | -0.058207 | 51179.0478 |  |  | 497Acres |  | 497 | Fully Billed |  | November |  | Closed
Alphonse | WOCOMPANY_009 | SDPLDEAL-165 | One time Project |  | Completed | 2025-12-19 | 2025-11-28 | Purchase Order | 2025-11-25 | 2025-12-25 | OWNER_001 | Renewables | Topography Survey: RGB, Hydrology | SPECTRA |  |  | 709081.3676 | 836716.0138 |  | 0 |  | 709081.3676 | 836716.0138 | 0 |  |  | 415Acers |  | 415 | Fully Billed |  | November
Alphonse | WOCOMPANY_009 | SDPLDEAL-166 | One time Project |  | Completed | 2025-11-07 | 2025-11-28 | Purchase Order | 2025-11-13 | 2025-12-03 | OWNER_001 | Renewables | Topography Survey: RGB, Hydrology | SPECTRA |  | SDPL/FY25-26/900 | 487112.7668 | 574793.0648 | 487116.0224 | 574796.9065 |  | -3.2556 | -3.8417 | 574796.9065 |  |  | 230Acres |  | 230 | Fully Billed |  | November
Obito | WOCOMPANY_023 | SDPLDEAL-167 | One time Project |  | Completed | 2026-01-06 | 2025-12-05 | Purchase Order | 2025-12-11 | 2025-12-31 | OWNER_003 | Mining | Mine survey | NONE |  |  | 1.2332 | 1.4552 |  | 0 |  | 1.2332 | 1.4552 | 0 |  |  | 40 Acres |  | 40 | [7 empty] | Update Required
Stewie Griffin | WOCOMPANY_029 | SDPLDEAL-168 | One time Project |  | Ongoing |  | 2025-12-17 | Purchase Order | 2025-12-22 | 2026-01-16 | OWNER_002 | Powerline | Thermography | NONE |  |  | 608584.2 | 718129.356 |  | 0 |  | 608584.2 | 718129.356 | 0 |  |  | 105 Towers |  | 105
Scooby-Doo | WOCOMPANY_002 | SDPLDEAL-169 | One time Project |  | Not Started |  | 2025-12-13 | Purchase Order | 2025-12-13 | 2026-01-31 | OWNER_003 | Mining | LiDAR Survey: LiDAR | NONE |  |  | 680726.4 | 803257.152 |  | 0 |  | 680726.4 | 803257.152 | 0 |  |  | 1 |  | 1
Sesshomaru | WOCOMPANY_017 | SDPLDEAL-170 | One time Project |  | Completed | 2026-01-06 | 2025-12-20 | Purchase Order | 2025-12-16 | 2026-01-31 | OWNER_003 | Renewables | Hydrology | NONE |  |  | 308300 | 363794 |  | 0 |  | 308300 | 363794 | 0 |  |  | 1 |  | 1 | [7 empty] | Update Required
Erwin | WOCOMPANY_021 | SDPLDEAL-171 | One time Project |  | Ongoing |  | 2025-12-17 | Purchase Order | 2025-12-22 | 2025-12-31 | OWNER_001 | Mining | Topography Survey: RGB, Raw images/videography | NONE |  |  | 425454 | 502035.72 |  | 0 |  | 425454 | 502035.72 | 0 |  |  | 10.5 KM |  | 10.5 | Not billed yet
Alias_160 | WOCOMPANY_051 | SDPLDEAL-172 | One time Project |  | Completed | 2025-12-23 | 2025-12-12 | Purchase Order | 2025-12-20 | 2025-12-31 | OWNER_001 | Mining | Topography Survey: RGB | SPECTRA |  |  | 53644.2 | 63300.156 |  | 0 |  | 53644.2 | 63300.156 | 0 |  |  | 300 HA |  | 300 | Not billed yet
Alias_160 | WOCOMPANY_051 | SDPLDEAL-173 | One time Project |  | Completed | 2025-12-23 | 2025-12-12 | Purchase Order | 2025-12-20 | 2025-12-31 | OWNER_001 | Mining | Topography Survey: RGB | SPECTRA |  |  | 51852.3604 | 61185.7853 |  | 0 |  | 51852.3604 | 61185.7853 | 0 |  |  | 290 |  | 290 | Not billed yet
Octopus | WOCOMPANY_002 | SDPLDEAL-174 | One time Project |  | Ongoing |  | 2025-12-20 | Purchase Order | 2025-12-20 | 2026-01-31 | OWNER_003 | Mining | Others | NONE |  |  | 43162 | 50931.16 |  | 0 |  | 43162 | 50931.16 | 0 |  |  | 1 |  | 1
Ben Tennyson | WOCOMPANY_033 | SDPLDEAL-175 | One time Project |  | Ongoing |  | 2025-12-22 | Email Confirmation | 2025-12-25 | 2026-01-15 | OWNER_003 | Renewables | Hydrology, Topography Survey: RGB | NONE |  |  | 289802 | 341966.36 |  | 0 |  | 289802 | 341966.36 | 0 |  |  | 1 |  | 1
Ben Tennyson | WOCOMPANY_033 | SDPLDEAL-176 | One time Project |  | Ongoing |  | 2025-12-22 | Email Confirmation | 2025-12-25 | 2026-01-15 | OWNER_003 | Renewables | Hydrology, Topography Survey: RGB | NONE |  |  | 289802 | 341966.36 |  | 0 |  | 289802 | 341966.36 | 0 |  |  | 1 |  | 1
Alphonse | WOCOMPANY_009 | SDPLDEAL-177 | Monthly Contract |  | Not Started |  | 2025-12-16 | Purchase Order | 2025-11-01 | 2026-03-31 | OWNER_005 | Renewables | Surveillance- needs continues monitoring | SPECTRA + DMO |  |  | 462450 | 545691 | 184980 | 218276.4 | 213910.872 | 277470 | 327414.6 | 4365.528 |  |  | 5 |  | 5
Whale | WOCOMPANY_004 | SDPLDEAL-178 | Proof of Concept |  | Completed | [5 empty] | OWNER_002 | Powerline | Thermography, LiDAR Survey: LiDAR, Powerline Inspection | SPECTRA |  |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  |  | 2 towers |  | 2
Squirtle | WOCOMPANY_049 | SDPLDEAL-179 | Proof of Concept |  | Ongoing |  | 2025-12-24 | Purchase Order | 2025-12-24 | 2025-12-31 | OWNER_002 | Powerline | Powerline Inspection | SPECTRA |  |  | 55494 | 65482.92 |  | 0 |  | 55494 | 65482.92 | 0 |  |  | L/s
Ben Tennyson | WOCOMPANY_033 | SDPLDEAL-180 | One time Project |  | Ongoing |  | 2025-12-29 | Email Confirmation | 2025-12-31 | 2026-01-31 | OWNER_003 | Renewables | Topography Survey: RGB, Hydrology | NONE |  |  | 295968 | 349242.24 |  | 0 |  | 295968 | 349242.24 | 0 |  |  | 1 |  | 1
Turtle | WOCOMPANY_024 | SDPLDEAL-181 | Proof of Concept |  | Details pending from Client |  | 2026-01-01 | Purchase Order | 2026-01-12 | 2026-02-12 | OWNER_004 | Mining | Mine survey | SPECTRA |  |  | 184980 | 218276.4 |  | 0 |  | 184980 | 218276.4 | 0 |  |  | 150000 |  | 150000 |  |  |  |  | Open
Bugs Bunny | WOCOMPANY_028 | SDPLDEAL-182 | One time Project |  | Not Started |  | 2026-01-12 | Email Confirmation | 2026-01-09 | 2026-03-31 | OWNER_003 | Railways | LiDAR Survey: LiDAR | NONE |  |  | 8986062.0288 | 10603553.194 |  | 0 |  | 8986062.0288 | 10603553.194 | 0 |  |  | 593 |  | 593
Bulbasaur | WOCOMPANY_050 | SDPLDEAL-185 | One time Project |  | Not Started |  | 2026-01-09 | Email Confirmation | 2026-01-12 | 2026-01-16 | OWNER_004 | Others | Others | SPECTRA |  |  | 139072.8968 | 164106.0182 | 164106.0182 | 193645.1015 | 69560.5698 | -25033.1214 | -29539.0833 | 124084.5317 | Priority |  | 7000 images |  | 7000
Timon | WOCOMPANY_046 | SDPLDEAL-186 | One time Project |  | Ongoing |  | 2026-01-06 | Purchase Order | 2026-01-13 | 2026-01-30 | OWNER_001 | Renewables | Others | NONE |  |  | 209027.4 | 246652.332 |  | 0 |  | 209027.4 | 246652.332 | 0 |  |  | 1 |  | 1 | Not billed yet
Ben Tennyson | WOCOMPANY_033 | SDPLDEAL-187 | One time Project |  | Not Started |  | 2026-01-09 | Purchase Order | 2026-01-19 | 2026-06-30 | OWNER_003 | Renewables | Others | NONE |  |  | 610434 | 720312.12 |  | 0 |  | 610434 | 720312.12 | 0 |  |  | 6 |  | 6
Ben Tennyson | WOCOMPANY_033 | SDPLDEAL-188 | One time Project |  | Not Started |  | 2026-01-09 | Purchase Order | 2026-01-19 | 2026-02-28 | OWNER_003 | Renewables | Others | NONE |  |  | 215810 | 254655.8 |  | 0 |  | 215810 | 254655.8 | 0 |  |  | 2 |  | 2
| WOCOMPANY_045 | SDPLDEAL-189 | Proof of Concept |  | Ongoing |  | 2026-01-09 | Purchase Order | 2026-01-17 | 2026-03-31 | OWNER_003 | Railways | Others | NONE |  |  | 1035854.087 | 1222307.8227 |  | 0 |  | 1035854.087 | 1222307.8227 | 0 |  |  | 30 |  | 30